## Sheet1
Checklist 5.0
Category | Sub Category | Type | Item
1.0 Pre-Job | 1.1 Drawings & Specifications | S&C | Construction docs/direction should have: Full Set of Working Drawings - Permit Application
1.0 Pre-Job | 1.1 Drawings & Specifications | S&C | Construction docs/direction should have: List of all drawings
1.0 Pre-Job | 1.1 Drawings & Specifications | S&C | Construction docs/direction should have: Construction Documents, Engineering, Finish Schedule, Conditions of Approval, SWPP. Sect.
1.0 Pre-Job | 1.1 Drawings & Specifications | S&C | Construction docs/direction should have: Written Specifications
1.0 Pre-Job | 1.1 Drawings & Specifications | S&C | Construction docs/direction should have: Bid instructions for subcontractors
1.0 Pre-Job | 1.1 Drawings & Specifications | S&C | Construction docs/direction should have: Copies of Permits for Demolition, Building, Grading, Tree
1.0 Pre-Job | 1.2 Communication | S&C | Contact List: Professionals - Architect/Engineer, SPECIAL Entities (such as) - Fish & Game/Water Quality/Army Corps of Engineers
1.0 Pre-Job | 1.2 Communication | S&C | Subcontractors - List of all subs, contact information, contract (scope of work)
1.0 Pre-Job | 1.3 Reports | S&C | Budget
1.0 Pre-Job | 1.4 Unusual Issues | Doc | Identify Outstanding Issues - city, county, utility
1.0 Pre-Job | 1.4 Unusual Issues | S&C | Superintendent evaluate "scope of work" for errors/omissions/deficiencies and identify
1.0 Pre-Job | 1.5 Schedule | Com | Project Schedule / Completion Date
1.0 Pre-Job | 1.5 Schedule | Com | Selection schedule
1.0 Pre-Job | 1.5 Schedule | Com | Walk-thru schedule
1.0 Pre-Job | 1.6 Safety | Com | Hold safety meeting every 2 weeks and maintain log of points covered
1.0 Pre-Job | 1.6 Safety | Com | Ensure subcontractors are in compliance with company safety plan
1.0 Pre-Job | 1.6 Safety | S&C | Keep stocked first-aid kit on site
1.0 Pre-Job | 1.6 Safety | Com | Keep records of hazardous materials on site
1.0 Pre-Job | 1.6 Safety | Com | Use accident report forms in the event of an injury or accident
1.0 Pre-Job | 1.6 Safety | S&C | Confirm all vehicles have audible back up signals
1.0 Pre-Job | 1.6 Safety | Com | Maintain list of emergency phone numbers
1.0 Pre-Job | 1.6 Safety | S&C | Maintain a clean and orderly job site, free of excess trash, debris, and scrap materials
1.0 Pre-Job | 1.6 Safety | S&C | Confirm that any materials are secure, orderly, and not obstructing anything
1.0 Pre-Job | 1.7 Risk Management | S&C | Maintain proper fire protection including certified fire extinguishers
1.0 Pre-Job | 1.7 Risk Management | S&C | Post "No-Trespassing Signs"
1.0 Pre-Job | 1.8 Strategic Planning | S&C | Identify components (windows, doors, garage doors, etc) rough-in sizes and set pre-order dates
2.0 Site Prep | 2.1 Erosion Control | Doc | Photograph Job Site
2.0 Site Prep | 2.1 Erosion Control | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
2.0 Site Prep | 2.1 Erosion Control | Com | Check SWIP requirements with civil engineer
2.0 Site Prep | 2.1 Erosion Control | S&C | Check existing property slope and verify required erosion control
2.0 Site Prep | 2.1 Erosion Control | Doc | Check adjacent property issues
2.0 Site Prep | 2.1 Erosion Control | S&C | Devices in place per plans
2.0 Site Prep | 2.1 Erosion Control | S&C | Maintenance of devices as needed
2.0 Site Prep | 2.2 Temporary Utilities | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
2.0 Site Prep | 2.2 Temporary Utilities | S&C | Location on building
2.0 Site Prep | 2.2 Temporary Utilities | S&C | Temporary power installation and location
2.0 Site Prep | 2.2 Temporary Utilities | S&C | Check site conditions related to utility plans
2.0 Site Prep | 2.2 Temporary Utilities | S&C | Ensure all requests for temporary and permanent utilities are submitted
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | S&C | Evaluate the site for abnormalities with drainage, existing utilities, easements, property line issues, trees/tree protection (arbonist?)
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | S&C | Verify easements, setbacks
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | S&C | Identify staging & access areas - barricade requirements
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | Doc | Evaluate surrounding property/neighborhood
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | S&C | Does existing site look similar to SITE PLAN?
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | S&C | Provide Construction Notice - contact, work times, trucking (off haul/deliveries, etc) to neighborhood
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | S&C | Provide jobsite signage with contacts, start-stop times,
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | Com | Communicate parking requirements to all visitors, subcontractors
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | S&C | Check FF Elevations relative to utility connections
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | S&C | Off Site - Check site connections with infastructure
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | S&C | Off Site - Check area for security issues
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | Doc | Off Site - Photograph existing conditions - especially streets & curbs
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | S&C | Off Site - Identify Logistics, access issues
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | S&C | Off Site - Identify hazards
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | Com | Schedule existing utility MARKING
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | Doc | Photograph existing SITE conditions
2.0 Site Prep | 2.3 Access, Staging Areas and Preliminary Tasks | S&C | Install chemical toilet/hand/eye wash facility
2.0 Site Prep | 2.4 Demolition | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
2.0 Site Prep | 2.5 Soil Testing | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
2.0 Site Prep | 2.5 Soil Testing | Com | Schedule and conduct soil testing as required
2.0 Site Prep | 2.5 Soil Testing | S&C | Review Soil Testing Report
3.0 Earthwork | 3.0 Earthwork - General | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
3.0 Earthwork | 3.0 Earthwork - General | Com | Meet with grading inspector
3.0 Earthwork | 3.0 Earthwork - General | Com | Coordination Meeting with all trades during this phase of construction prior to start
3.0 Earthwork | 3.1 Clear & Rough Grading | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
3.0 Earthwork | 3.1 Clear & Rough Grading | Doc | Clearing - Check tree tags prior to removal/retain tree tags for record
3.0 Earthwork | 3.1 Clear & Rough Grading | Doc | Clearing - Ensure remaining trees are protected
3.0 Earthwork | 3.1 Clear & Rough Grading | Doc | Clearing - Check plans for boundary of work
3.0 Earthwork | 3.1 Clear & Rough Grading | Doc | Clearing - Review conditions of approval
3.0 Earthwork | 3.1 Clear & Rough Grading | Com | Alert any public utilities no less than two days before any excavation or underground tenching. Confirm that all existing pipes and utility lines are identified and marked.
3.0 Earthwork | 3.1 Clear & Rough Grading | Doc | Make sure trench shoring is used to support walls and faces of excavations exceeding five feet. If workers are entering and working in trenches, make sure all loose material is kept back a minimum of two feet. Make sure workers use ladders to enter trenches or excavations deeper than four feet.
3.0 Earthwork | 3.2 Foundation Layout | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
3.0 Earthwork | 3.2 Foundation Layout | S&C | Check forms vs plans
3.0 Earthwork | 3.2 Foundation Layout | S&C | Check corners are square
3.0 Earthwork | 3.2 Foundation Layout | S&C | Measure forms and verify they're correct with plans
3.0 Earthwork | 3.3 Excavation | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
3.0 Earthwork | 3.3 Excavation | S&C | Calculate number of trucks needed for dirt import or export
3.0 Earthwork | 3.3 Excavation | S&C | Caluculate estimated loading time (inc. stand by) for dirt import or export
3.0 Earthwork | 3.3 Excavation | S&C | Confirm truck round trip time (cycle time)
3.0 Earthwork | 3.3 Excavation | Doc | Before the dirt is import or exported: Keep a daily log and load count. Document and confirm load counts at the end of each day. Make sure the counts from the jobsite, truck­ing operation, and export site agree
3.0 Earthwork | 3.4 Pad/Foundation Preparation | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
3.0 Earthwork | 3.5 Shoring and Trenching | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
3.0 Earthwork | 3.5 Shoring and Trenching | S&C | Confirm that the framing, shoring, and formwork are sufficient for the expected loads during construction
3.0 Earthwork | 3.6 Structural Retaining Walls | Com | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
3.0 Earthwork | 3.6 Structural Retaining Walls | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
3.0 Earthwork | 3.6 Structural Retaining Walls | S&C | Check waterproof and drainage specifications vs installation
3.0 Earthwork | 3.6 Structural Retaining Walls | Com | Schedule observations and inspections
3.0 Earthwork | 3.7 Staking | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
4.0 Utilities | 4.0 Utilities - General | Com | Have all utilities marked
4.0 Utilities | 4.0 Utilities - General | Com | Coordination Meeting with all trades during this phase of construction prior to start
4.0 Utilities | 4.0 Utilities - General | S&C | When utilities are being installed, make sure you have gas stub-outs marked on footings so gas company will know where to run their line. Note: Prior to concrete, make sure gas, electric, and television sleeves are in place (usually in garages) at utility boxes or panels. Confirm locations of utilities prior to concrete pour.
4.0 Utilities | 4.0 Utilities - General | Com | Assure submittals in process
4.0 Utilities | 4.1 Water | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
4.0 Utilities | 4.2 Sewer | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
4.0 Utilities | 4.3 Electric | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
4.0 Utilities | 4.4 Gas | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
4.0 Utilities | 4.5 Well | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
4.0 Utilities | 4.6 Septic System | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
4.0 Utilities | 4.7 Storm Drainage | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
4.0 Utilities | 4.8 Staking | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
5.0 Foundation | 5.1 Foundation - General | Com | Have all utilities marked
5.0 Foundation | 5.1 Foundation - General | Com | Pad certification
5.0 Foundation | 5.1 Foundation - General | Com | Coordination Meeting with all trades during this phase of construction prior to start
5.0 Foundation | 5.1 Foundation - General | S&C | Identify Electrical Panel and Ufer Ground locations
5.0 Foundation | 5.1 Foundation - General | Com | Review foundation logistics with subcontractors
5.0 Foundation | 5.1 Foundation - General | S&C | Review plans for garage and rooms elevation (slope, raised, lowered) - check for special elevation requirements (tile, etc)
5.0 Foundation | 5.1 Foundation - General | S&C | Verify foundation is staked per plans
5.0 Foundation | 5.1 Foundation - General | S&C | Check all hold downs, MEPs
5.0 Foundation | 5.1 Foundation - General | S&C | Drainage: Check downspout layout; Check outfalls and review with contractor; Raised floor full sub drain system, 4" minimum pipe system with a 12" minimum clay cap, trench to be flow lined to outfall.
5.0 Foundation | 5.1 Foundation - General | S&C | Confirm that the concrete load tickets indicate the correct type of concrete, cement sack mix, and water ratio
5.0 Foundation | 5.2 Underfloor Plumbing | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
5.0 Foundation | 5.2 Underfloor Plumbing | S&C | Locate floor plumbing and island/peninsula plumbing
5.0 Foundation | 5.3 Underfloor HVAC | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
5.0 Foundation | 5.4 Underfloor Electrical | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
5.0 Foundation | 5.4 Underfloor Electrical | S&C | Locate floor electrical and island/peninsula electical
5.0 Foundation | 5.5 Raised Foundation | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
5.0 Foundation | 5.5 Raised Foundation | S&C | Verify correct elevations, set backs, brick ledges,
5.0 Foundation | 5.5 Raised Foundation | S&C | Verify concrete mix, pour, finish per specifications
5.0 Foundation | 5.5 Raised Foundation | Com | Schedule inspection as needed
5.0 Foundation | 5.6 PT Slab Foundation | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
5.0 Foundation | 5.6 PT Slab Foundation | S&C | Check cable specifications
5.0 Foundation | 5.6 PT Slab Foundation | S&C | Verify concrete mix / finish
5.0 Foundation | 5.6 PT Slab Foundation | S&C | Double check FF Elevation
5.0 Foundation | 5.7 Garage Slab | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
5.0 Foundation | 5.7 Garage Slab | S&C | Check slope and elevation
5.0 Foundation | 5.7 Garage Slab | S&C | Layout score joints and wind lips
5.0 Foundation | 5.7 Garage Slab | S&C | Check expansion material
5.0 Foundation | 5.7 Garage Slab | S&C | Isolate from foundation as necessary
5.0 Foundation | 5.7 Garage Slab | S&C | Verify concrete mix, pour, finish per specifications
5.0 Foundation | 5.8 Basement Slab | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
5.0 Foundation | 5.9 Waterproofing | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
5.0 Foundation | 5.10 Backfill | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
5.0 Foundation | 5.11 Staking | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
6.0 Framing | 6.0 Framing - General | Com | Coordination Meeting with all trades during this phase of construction prior to start
6.0 Framing | 6.0 Framing - General | S&C | Prior to the framing inspection, check draft-stops and furnace platforms. Note: Block or draft-stop as required.
6.0 Framing | 6.0 Framing - General | S&C | Confirm rough openings - verify with owner, architect, suppliers, subcontractors. Check against windows, doors, equipment
6.0 Framing | 6.1 Framing Pre-Construction | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
6.0 Framing | 6.1 Framing Pre-Construction | S&C | Ensure adequate clearance from earth to wood contact
6.0 Framing | 6.1 Framing Pre-Construction | S&C | Review structural plans for conformance; check to see that the structural plans are being followed and that they are married to the architectural
6.0 Framing | 6.1 Framing Pre-Construction | S&C | Verify galvanized connectors are used with pressure treated materials
6.0 Framing | 6.1 Framing Pre-Construction | S&C | MEPs - coordinate and check layout with subcontractors and structural engineer as needed
6.0 Framing | 6.2 Framing Basement | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
6.0 Framing | 6.3 Framing Floor | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
6.0 Framing | 6.3 Framing Floor | S&C | Make sure the under floor is clean of all debris
6.0 Framing | 6.3 Framing Floor | S&C | Under floor venting - make sure code is exceeded for cubic ?? inches to square feet with cross ventilation and no dead cells
6.0 Framing | 6.3 Framing Floor | S&C | Beams - verify with plans & specs. Verify proper fastening procedures.
6.0 Framing | 6.3 Framing Floor | S&C | Verify galvanized connectors are used with pressure treated materials
6.0 Framing | 6.3 Framing Floor | S&C | Ensure there is an under floor access within 25 feet of any plumbing (as required for crawl space construction)
6.0 Framing | 6.4 Framing Wall | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
6.0 Framing | 6.4 Framing Wall | S&C | Beams - verify with plans & specs. Verify proper fastening procedures.
6.0 Framing | 6.4 Framing Wall | S&C | Check for all blocking (cabinets, hardware, accessories, etc.)
6.0 Framing | 6.4 Framing Wall | S&C | Termite Flashing; make sure all exterior doors are protected and conforms to plans
6.0 Framing | 6.4 Framing Wall | S&C | Verify galvanized connectors are used with pressure treated materials
6.0 Framing | 6.4 Framing Wall | Com | Confirm all shear wall and roof nailing schedules are correct
6.0 Framing | 6.4 Framing Wall | S&C | Ensure anchor bolts and hold downs conform to plans
6.0 Framing | 6.5 Framing Roof | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
6.0 Framing | 6.5 Framing Roof | Com | Confirm all shear wall and roof nailing schedules are correct
6.0 Framing | 6.5 Framing Roof | S&C | Under shots; make sure all roof cavities and blocked and protected from animal infiltation
6.0 Framing | 6.5 Framing Roof | S&C | Bracing and blocking: double check all bracing and blocking trusses, backing for hardware and fixutres, shampoo niches, etc.
6.0 Framing | 6.5 Framing Roof | S&C | Beams - verify with plans & specs. Verify proper fastening procedures.
6.0 Framing | 6.6 Framing Stairs | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
6.0 Framing | 6.7 Framing Miscellaneous | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
6.0 Framing | 6.7 Framing Miscellaneous | S&C | Have a cabinet walk with the client and subcontractor at start of MEPs when possible.
6.0 Framing | 6.7 Framing Miscellaneous | S&C | Structural Steel: Make sure the layout is accurate and measurements are confirmed by the framing contractor and conform to the plans
6.0 Framing | 6.7 Framing Miscellaneous | S&C | Structural Steel: Make sure all field welds are certified
6.0 Framing | 6.7 Framing Miscellaneous | S&C | Structural Steel: Make sure all support plates are dry packed with non-shrink grout befor covering
6.0 Framing | 6.7 Framing Miscellaneous | S&C | Lay out job to protect the structure both from water infiltration and for aesthetics
6.0 Framing | 6.7 Framing Miscellaneous | S&C | Make sure all sheet metal is installed in a clean workman like manner
7.0 Rough Trades | 7.0 Scaffold | S&C | Coordination Meeting with all trades during this phase of construction prior to start
7.0 Rough Trades | 7.0 Scaffold | S&C | Make sure scaffolding is adequate for its intended purpose, and in good condition. Make sure footings are protected against movement. Make sure the frame is sound, rigid, and capable of supporting the intended load.
7.0 Rough Trades | 7.0 Scaffold | S&C | Make sure Planking does not extend less than six or more than twelve inches over the ends of frames. Make sure planking overlaps at least twelve inches
7.0 Rough Trades | 7.0 Scaffold | S&C | Make sure poles, legs, and frames are plumb, with adequate cross bracing to prevent swaying. Make sure scaffolding is secured to the building to prevent if from falling down or becoming displaced.
7.0 Rough Trades | 7.0 Scaffold | S&C | Make sure guardrails and toe boards are provided on any scaffold, wall or floor opening six feet or more above the floor or ground. Guardrails should be forty-two inches above the floor or planking.
7.0 Rough Trades | 7.0 Scaffold | S&C | Make sure guardrail can withstand a minimum impact of two hundred pounds.
7.0 Rough Trades | 7.1 Fireplace(s) Rough-In | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
7.0 Rough Trades | 7.1 Fireplace(s) Rough-In | S&C | Make sure the metal fireplace supplier or mason comes out prior to framing. Confirm with the supplier or framer all floor openings and chimney ties.
7.0 Rough Trades | 7.1 Fireplace(s) Rough-In | S&C | Layout hearth, opening, height and any other component that might be used in and around the fireplace including the firebrick and design with Client and or Designer.
7.0 Rough Trades | 7.1 Fireplace(s) Rough-In | S&C | Coordinate with electrician for switch layout or any special electrical needs.
7.0 Rough Trades | 7.1 Fireplace(s) Rough-In | S&C | Layout flooring to fireplace transition
7.0 Rough Trades | 7.2 HVAC Rough-In | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
7.0 Rough Trades | 7.2 HVAC Rough-In | S&C | Check for the following: Make sure heating plans have been approved.
7.0 Rough Trades | 7.2 HVAC Rough-In | S&C | Check for the following: Read the contract. Make sure the system being installed is according to the approved plan.
7.0 Rough Trades | 7.2 HVAC Rough-In | S&C | Check for the following: Check for proper size of duct, insulation, and clearances.
7.0 Rough Trades | 7.2 HVAC Rough-In | S&C | Check for the following: Check register locations and return air vent sizes.
7.0 Rough Trades | 7.2 HVAC Rough-In | S&C | Check for the following: Check for proper hangers or straps.
7.0 Rough Trades | 7.2 HVAC Rough-In | S&C | Make sure all supplies and returns are laid out in an efficient aesthetical way
7.0 Rough Trades | 7.2 HVAC Rough-In | S&C | Review both thermostat and supply/return registers are laid out with the owner
7.0 Rough Trades | 7.3 Plumbing Rough-In | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
7.0 Rough Trades | 7.3 Plumbing Rough-In | S&C | Check fixture layout with designer/owner for placement
7.0 Rough Trades | 7.3 Plumbing Rough-In | S&C | Make sure all vents are to the rear of the structure and not visible from the front of the house
7.0 Rough Trades | 7.3 Plumbing Rough-In | S&C | Make sure all hose bibs, BBQ stubs, condensate are laid out as directed by designer/owner
7.0 Rough Trades | 7.3 Plumbing Rough-In | S&C | Make sure all waste has cast iron risers between floors
7.0 Rough Trades | 7.3 Plumbing Rough-In | S&C | Make sure all exterior flashing is complete
7.0 Rough Trades | 7.3 Plumbing Rough-In | S&C | Make sure all pipes are protected from penetration in the framing
7.0 Rough Trades | 7.4 Electrical Rough-In | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
7.0 Rough Trades | 7.4 Electrical Rough-In | Com | Make sure electrician has an exterior siding and shear panel schedule so he can set his boxes out accordingly
7.0 Rough Trades | 7.4 Electrical Rough-In | S&C | Check location of all outlets (television, boxes, and lights)
7.0 Rough Trades | 7.4 Electrical Rough-In | S&C | Check for proper spacing from edge of framing lumber. (Two-inch minimum.)
7.0 Rough Trades | 7.4 Electrical Rough-In | S&C | Check boxes against casing width
7.0 Rough Trades | 7.4 Electrical Rough-In | S&C | Make sure to allow layout and clearances are adequate for finishes
7.0 Rough Trades | 7.4 Electrical Rough-In | Com | Schedule electrical walk with the designer/owner prior to starting
7.0 Rough Trades | 7.4 Electrical Rough-In | S&C | Make sure all panels are in a convenient code worthy location
7.0 Rough Trades | 7.4 Electrical Rough-In | S&C | Make sure all fixtures are anchored adequately for the weight of the fixture
7.0 Rough Trades | 7.4 Electrical Rough-In | S&C | Make sure electrician tests all circuits prior to sheetrock
7.0 Rough Trades | 7.4 Electrical Rough-In | S&C | Check number of outlets / lights per circuit
7.0 Rough Trades | 7.5 Fire Protection | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
7.0 Rough Trades | 7.5 Fire Protection | S&C | Make sure all shop drawings are approved
7.0 Rough Trades | 7.5 Fire Protection | S&C | Have electrical can lights laid out before installation
7.0 Rough Trades | 7.5 Fire Protection | S&C | Find a good location for the fire service
7.0 Rough Trades | 7.5 Fire Protection | S&C | Lay out all fire heads to work with can lights, ceiling beams and any protruding items in the ceiling
7.0 Rough Trades | 7.5 Fire Protection | S&C | Check layout against required distances from lights, registers, etc.
7.0 Rough Trades | 7.6 Central Vacuum Rough-In | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
7.0 Rough Trades | 7.7 Security System Rough-In | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
7.0 Rough Trades | 7.7 Security System Rough-In | Com | Schedule walk thru with client lay out keypads, speaks, controls, etc.
7.0 Rough Trades | 7.7 Security System Rough-In | S&C | Lay out patch panel in a convenient location
7.0 Rough Trades | 7.7 Security System Rough-In | S&C | Make sure alarm contacts are not installed in a door or window that would compromise the manufacturer’s warranty or cause a leak issue
7.0 Rough Trades | 7.8 FRAMING PRE-INSPECTION | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
7.0 Rough Trades | 7.9 INSPECTION | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
8.0 Roof | 8.0 Roof - General | S&C | Run roof flashings, roof-to-wall metal, and valley flashings
8.0 Roof | 8.0 Roof - General | S&C | Check for correct gravel stop
8.0 Roof | 8.0 Roof - General | S&C | Check chimney flashings
8.0 Roof | 8.0 Roof - General | S&C | Make sure all roof vent flashings have been supplied by plumbing, heating and sheet metal
8.0 Roof | 8.0 Roof - General | S&C | Lay out job to protect the structure both from water infiltration and for aesthetics
8.0 Roof | 8.0 Roof - General | S&C | Make sure all sheet metal is installed in a clean workman like manner
8.0 Roof | 8.0 Roof - General | S&C | Install plaster screed or foundation metal: Check for correct type of metal
8.0 Roof | 8.0 Roof - General | S&C | Install plaster screed or foundation metal: Check for proper lap and nailing
8.0 Roof | 8.0 Roof - General | S&C | Install plaster screed or foundation metal: Check for proper corners
8.0 Roof | 8.0 Roof - General | S&C | Install plaster screed or foundation metal: Check for proper caulking
8.0 Roof | 8.0 Roof - General | S&C | Make sure overflow scuppers are installed on flat roofs and decks
8.0 Roof | 8.0 Roof - General | S&C | Make sure downspouts are properly connected to deck drains
8.0 Roof | 8.0 Roof - General | S&C | Check range hood vent location
8.0 Roof | 8.0 Roof - General | S&C | Check bath fan housing vent
8.0 Roof | 8.0 Roof - General | S&C | Check attic ventilation
8.0 Roof | 8.0 Roof - General | S&C | Review layout for all penetrations with subcontractor prior and keep as many as possible to the rear of the structure.
8.0 Roof | 8.0 Roof - General | S&C | Make sure coursing is straight when using any type of shingles.
8.0 Roof | 8.0 Roof - General | S&C | Review roof to wall details and use Z bar detail where needed.
8.0 Roof | 8.0 Roof - General | S&C | Review valley type with client/architect.
8.0 Roof | 8.0 Roof - General | S&C | Make sure gutter and rake flashing is used.
8.0 Roof | 8.0 Roof - General | S&C | Make sure all under shots are closed in.
8.0 Roof | 8.1 Asphalt Shingle | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
8.0 Roof | 8.2 Tile | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
8.0 Roof | 8.2 Tile | S&C | When using concrete or clay tile use 2 layers of 30lb felt.
8.0 Roof | 8.3 Flat Roof | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.0 Exterior Finish - General | S&C | Coordination Meeting with all trades during this phase of construction prior to start
9.0 Exterior Finish | 9.0 Exterior Finish - General | S&C | Waterproof build with 2 layers of 60 minute building paper.
9.0 Exterior Finish | 9.0 Exterior Finish - General | S&C | Review all window and door flashings including electrical and plumbing for consistency in method of waterproofing.
9.0 Exterior Finish | 9.0 Exterior Finish - General | S&C | Make sure all cuts are primed and sealed.
9.0 Exterior Finish | 9.0 Exterior Finish - General | S&C | Layout trim blocks for electrical fixtures.
9.0 Exterior Finish | 9.0 Exterior Finish - General | S&C | Use Z bar flashing over windows and doors, when possible pre-paint with window manufacturer’s color.
9.0 Exterior Finish | 9.0 Exterior Finish - General | S&C | Use Z bar flashing over belly bands and like exterior trim that is not lapped or interlocking. Do not interrupt building paper with Z bar.
9.0 Exterior Finish | 9.1 Scaffolding | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.2 Exterior Doors | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.2 Exterior Doors | Com | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
9.0 Exterior Finish | 9.2 Exterior Doors | S&C | Confirm all installations are flashed, installed correctly and in correct openings, and check for operation per plans
9.0 Exterior Finish | 9.2 Exterior Doors | S&C | Make sure all window and door openings are flashed properly using door pans and head flashings
9.0 Exterior Finish | 9.3 Windows | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.3 Windows | S&C | Confirm all installations are flashed, installed correctly and in correct openings, and check for operation per plans
9.0 Exterior Finish | 9.3 Windows | S&C | Make sure all window and door openings are flashed properly using door pans and head flashings
9.0 Exterior Finish | 9.4 Skylights | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.4 Skylights | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
9.0 Exterior Finish | 9.4 Skylights | S&C | Confirm all installations are flashed, installed correctly and in correct openings, and check for operation per plans
9.0 Exterior Finish | 9.4 Skylights | S&C | Make sure all window and door openings are flashed properly using door pans and head flashings
9.0 Exterior Finish | 9.5 Garage Doors | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.6 Exterior Finish - Hardi Board | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.6 Exterior Finish - Hardi Board | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
9.0 Exterior Finish | 9.6 Exterior Finish - Hardi Board | S&C | When using Hardi siding use finish nails at butt joints, back joints with building paper.
9.0 Exterior Finish | 9.7 Exterior Finish - Vinyl | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.7 Exterior Finish - Vinyl | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
9.0 Exterior Finish | 9.8 Exterior Finish - Batt and Board | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.8 Exterior Finish - Batt and Board | S&C | Layout batts prior to installation. Should be symmetrical.
9.0 Exterior Finish | 9.8 Exterior Finish - Batt and Board | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
9.0 Exterior Finish | 9.9 Exterior Finish - Paint | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.9 Exterior Finish - Paint | S&C | Check selections against paint cans and ensure proper colors being applied
9.0 Exterior Finish | 9.9 Exterior Finish - Paint | Com | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | Com | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | S&C | check selections against paint cans and ensure proper colors being applied
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | S&C | receive approval on stucco finish and color using sample boards from client before starting
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | S&C | layout expansion joints with client
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | S&C | Use primer and 2 coats of finish on all surfaces.
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | S&C | Semi gloss on ext. trim and satin on body of house
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | S&C | Prime all cuts and caulk all joints
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | S&C | Before Lathing: Read the contract thoroughly, especially the specification section.
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | S&C | Before Lathing: Check for correct gauge of string wire.
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | S&C | Before Lathing: Check for furring nails or prefurred lath. Note: Properly installed furring nails prevent cracks in the plaster.
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | S&C | Before Lathing: Check for waterproof sheathing paper with proper lap (six inches) and shear stapling. Check for proper lap of wire (three inches).
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | S&C | Before Lathing: Check for woven wire lath.
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | S&C | Before Lathing: Check type of nails and nailing schedule.
9.0 Exterior Finish | 9.10 Exterior Finish - Stucco | S&C | Before Lathing: Make sure windows, doors, and meter cabinets are flashed prior to lath.
9.0 Exterior Finish | 9.11 Exterior Finish - Masonry (Brick veneer/stone) | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.11 Exterior Finish - Masonry (Brick veneer/stone) | Com | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
9.0 Exterior Finish | 9.11 Exterior Finish - Masonry (Brick veneer/stone) | S&C | Make sure the selected materials are being used including the selected mortar and review these with the client.
9.0 Exterior Finish | 9.11 Exterior Finish - Masonry (Brick veneer/stone) | S&C | Review selection and layout with the Client/ Designer/ Architect.
9.0 Exterior Finish | 9.11 Exterior Finish - Masonry (Brick veneer/stone) | Com | Review waterproofing details and cap flashings at wainscot with subcontractor.
9.0 Exterior Finish | 9.11 Exterior Finish - Masonry (Brick veneer/stone) | S&C | Make sure all masonry veneer is installed to grade.
9.0 Exterior Finish | 9.11 Exterior Finish - Masonry (Brick veneer/stone) | S&C | Never install veneer over a floating concrete slab
9.0 Exterior Finish | 9.11 Exterior Finish - Masonry (Brick veneer/stone) | S&C | Review reinforcement with subcontractor before work starts.
9.0 Exterior Finish | 9.11 Exterior Finish - Masonry (Brick veneer/stone) | S&C | Make sure the layout and lay up are the correct and approved application.
9.0 Exterior Finish | 9.11 Exterior Finish - Masonry (Brick veneer/stone) | S&C | Review plans to confirm the correct layout and structural applications are being applied.
9.0 Exterior Finish | 9.11 Exterior Finish - Masonry (Brick veneer/stone) | S&C | When installing an exterior cooking/kitchen area make sure to locate and layout, utilities, appliances, BBQ, Pizza oven, Fireplace etc., always review with structural plans and make sure the structural and architectural plans are married.
9.0 Exterior Finish | 9.12 Exterior Finish - Accessories | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.12 Exterior Finish - Accessories | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
9.0 Exterior Finish | 9.13 Decks | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
9.0 Exterior Finish | 9.13 Decks | S&C | Pre-deck coating inspection: Make sure all holes are plugged.
9.0 Exterior Finish | 9.13 Decks | S&C | Pre-deck coating inspection: Make sure all flashings are properly installed.
9.0 Exterior Finish | 9.13 Decks | S&C | Pre-deck coating inspection: Make sure crickets are installed prior to preparing decks for water­proofing, to ensure proper drainage.
9.0 Exterior Finish | 9.13 Decks | S&C | Pre-deck coating inspection: Check grade and type of preservative used in wood.
9.0 Exterior Finish | 9.13 Decks | S&C | Pre-deck coating inspection: Make sure subdeck is dry prior to application of waterproofing materials.
9.0 Exterior Finish | 9.13 Decks | S&C | review details on all plans and specifications before starting
9.0 Exterior Finish | 9.13 Decks | S&C | make sure the substrate is sloped towards the drain
9.0 Exterior Finish | 9.13 Decks | S&C | screw down substrate per water proofing manufacturers specifications
9.0 Exterior Finish | 9.13 Decks | S&C | Follow manufacturer’s recommendations for installation of waterproofing membrane.
9.0 Exterior Finish | 9.13 Decks | S&C | Install membrane 6 inches above all doors and under doors.
9.0 Exterior Finish | 9.13 Decks | S&C | Review railing systems and avoid penetrations when possible.
10.0 Interior Finishes | 10.0 Interior Finish - General | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.0 Interior Finish - General | Com | Coordination Meeting with all trades during this phase of construction prior to start
10.0 Interior Finishes | 10.0 Interior Finish - General | Doc | Photograph all walls before sheetrock
10.0 Interior Finishes | 10.0 Interior Finish - General | Doc | Photograph and areas especially plumbing for documentation
10.0 Interior Finishes | 10.1 Insulation | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.1 Insulation | S&C | Make sure insulation is properly installed—with the paper facing the heat space
10.0 Interior Finishes | 10.1 Insulation | S&C | Check for complete air infiltration, draft-stopping, or caulking, as required
10.0 Interior Finishes | 10.1 Insulation | S&C | Refer to title 24 for insulation specifications
10.0 Interior Finishes | 10.1 Insulation | S&C | Keep soffit vents clear of insulation
10.0 Interior Finishes | 10.1 Insulation | S&C | Make sure all penetrations and gaps are filled with foam sealant
10.0 Interior Finishes | 10.2 Fire Rating Requirements | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.3 Drywall | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.3 Drywall | Com | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.3 Drywall | Doc | Photograph all walls before sheetrock
10.0 Interior Finishes | 10.3 Drywall | Doc | Photograph and areas especially plumbing for documentation
10.0 Interior Finishes | 10.3 Drywall | S&C | Check all acoustical and fire rating requirements
10.0 Interior Finishes | 10.3 Drywall | S&C | Check contract and plans for any special party or firewall conditions
10.0 Interior Finishes | 10.3 Drywall | S&C | Check for proper size, type, and nailing schedule
10.0 Interior Finishes | 10.3 Drywall | S&C | When installing resilient drywall channels: Check contract for correct channels.
10.0 Interior Finishes | 10.3 Drywall | S&C | When installing resilient drywall channels: Make sure screws and nails are per code and plans.
10.0 Interior Finishes | 10.3 Drywall | S&C | When installing resilient drywall channels: Check installation per code, contract, and manufacturer's specifications.
10.0 Interior Finishes | 10.3 Drywall | S&C | Check contract and plans for special conditions such as party walls, special caulking, and nailing or screwing requirements.
10.0 Interior Finishes | 10.3 Drywall | S&C | Check type ("X," "CD," regular, or water resistant) and size (one half-inch or five-eighths-inch).
10.0 Interior Finishes | 10.3 Drywall | S&C | Check corner bead for proper attachment and plumb.
10.0 Interior Finishes | 10.3 Drywall | S&C | After drywall is stocked, make sure window panels and mullions have been reinstalled properly and no damage has been done to doors or windows.
10.0 Interior Finishes | 10.3 Drywall | S&C | Make sure medicine cabinets, outlets, and attic accesses are not covered.
10.0 Interior Finishes | 10.3 Drywall | S&C | Make sure all drywall is installed 8” above all rough shower pans
10.0 Interior Finishes | 10.3 Drywall | S&C | Make sure special screws and joint compound is used at all wet walls
10.0 Interior Finishes | 10.3 Drywall | S&C | Use 5/8” or ½” ceiling board on ceilings throughout.
10.0 Interior Finishes | 10.3 Drywall | S&C | Use prep coat or flat wall primer before texture
10.0 Interior Finishes | 10.4 Interior Doors Installation | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.4 Interior Doors Installation | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.4 Interior Doors Installation | S&C | Adjust door heights with floor finishes and make all doors the same height.
10.0 Interior Finishes | 10.5 Finish Carpentry | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.5 Finish Carpentry | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.5 Finish Carpentry | S&C | Review all trim and layout of specialty areas 3 weeks before starting.
10.0 Interior Finishes | 10.5 Finish Carpentry | S&C | Review details and selections with the client and subcontractor before starting.
10.0 Interior Finishes | 10.5 Finish Carpentry | S&C | Layout scope in each room and adjust for clearances.
10.0 Interior Finishes | 10.6 Interior Paint | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.6 Interior Paint | S&C | Check selections against paint cans and ensure proper colors being applied
10.0 Interior Finishes | 10.6 Interior Paint | S&C | Confirm the list of materials and number of coats of paint in the contract
10.0 Interior Finishes | 10.6 Interior Paint | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.6 Interior Paint | S&C | Always tint primer finish wall color.
10.0 Interior Finishes | 10.6 Interior Paint | S&C | Prime walls and ceilings before starting interior trim and tile.
10.0 Interior Finishes | 10.6 Interior Paint | S&C | Prime all doors on six edges
10.0 Interior Finishes | 10.7 Hardwood | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.7 Hardwood | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.7 Hardwood | S&C | Verify correct sealant before installation
10.0 Interior Finishes | 10.8 Cabinets | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.8 Cabinets | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.8 Cabinets | S&C | Confirm proper hinge type
10.0 Interior Finishes | 10.8 Cabinets | S&C | Check for proper toe-kicks and scribe molding.
10.0 Interior Finishes | 10.8 Cabinets | S&C | Check cabinet and counter top heights.
10.0 Interior Finishes | 10.8 Cabinets | S&C | Check for full partitions.
10.0 Interior Finishes | 10.8 Cabinets | S&C | Check door stiffeners at pantries and broom closets. Replace any warped cabinet doors.
10.0 Interior Finishes | 10.8 Cabinets | S&C | Check nailing and alignment of rough top. Make sure holes are cut properly for all sinks and appliances. Make sure sink templates have been supplied by the plumber, and appliance cutouts by the supplier.
10.0 Interior Finishes | 10.8 Cabinets | S&C | Check refrigerator, oven, stove, and dishwasher space openings.
10.0 Interior Finishes | 10.8 Cabinets | S&C | Check margins at window openings.
10.0 Interior Finishes | 10.8 Cabinets | S&C | Review installation with client and subcontractor before starting.
10.0 Interior Finishes | 10.8 Cabinets | S&C | Make sure all HVAC vents at the toe have boots.
10.0 Interior Finishes | 10.8 Cabinets | S&C | Review appliances with subcontractor and client before starting.
10.0 Interior Finishes | 10.8 Cabinets | S&C | Review clearances between upper and lowers (18”) and hood to cooking surface and kitchen.
10.0 Interior Finishes | 10.9 Countertops | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.9 Countertops | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.9 Countertops | S&C | Review materials and installation with the client and subcontractor before starting.
10.0 Interior Finishes | 10.9 Countertops | S&C | Double check critical items such as edge details, overhangs.
10.0 Interior Finishes | 10.9 Countertops | S&C | When using slab material make sure seams are placed in acceptable positions, such as at center of sinks, always review with the client before the slabs are fabricated especially the placement of under mount sinks.
10.0 Interior Finishes | 10.9 Countertops | S&C | Always make sure you have adequate room between sink and backslash for your faucets etc.
10.0 Interior Finishes | 10.9 Countertops | S&C | Review backsplash layout.
10.0 Interior Finishes | 10.9 Countertops | S&C | Review tile layout at all counters.
10.0 Interior Finishes | 10.9 Countertops | S&C | Protect all areas when complete.
10.0 Interior Finishes | 10.10 Floor Tile | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.10 Floor Tile | S&C | Complete sheetrock before installing shower pan membrane.
10.0 Interior Finishes | 10.10 Floor Tile | S&C | Review all materials and layouts with the client and subcontractor before starting any work
10.0 Interior Finishes | 10.10 Floor Tile | S&C | Shower pan waterproofing systems should be of solid sheet type material (Coraloy) and not a liquid applied material.
10.0 Interior Finishes | 10.10 Floor Tile | S&C | Make sure substrate has sufficient slope to drain under waterproof membrane.
10.0 Interior Finishes | 10.10 Floor Tile | S&C | Check floor heights with adjacent rooms and materials to ensure a smooth, level transition room to room and brea all material changes under doors when possible.
10.0 Interior Finishes | 10.10 Floor Tile | S&C | Always protect tiled areas when complete.
10.0 Interior Finishes | 10.11 Wall Tile | S&C | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.11 Wall Tile | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.11 Wall Tile | S&C | Review all materials and layouts with the client and subcontractor before starting any work including shampoo niches.
10.0 Interior Finishes | 10.11 Wall Tile | S&C | Always protect tiled areas when complete.
10.0 Interior Finishes | 10.12 Shower Doors, Mirrors, Towel Bars, Medicine Cabinets | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.12 Shower Doors, Mirrors, Towel Bars, Medicine Cabinets | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.12 Shower Doors, Mirrors, Towel Bars, Medicine Cabinets | S&C | Check channels and finish. Make sure all edges are polished, not seamed.
10.0 Interior Finishes | 10.12 Shower Doors, Mirrors, Towel Bars, Medicine Cabinets | S&C | Check mirror color, type, finish, and thickness (one-quarter-inch, three sixteenths-inch).
10.0 Interior Finishes | 10.12 Shower Doors, Mirrors, Towel Bars, Medicine Cabinets | S&C | Check wall and ceiling reveals.
10.0 Interior Finishes | 10.12 Shower Doors, Mirrors, Towel Bars, Medicine Cabinets | S&C | Check for chips on all four corners.
10.0 Interior Finishes | 10.12 Shower Doors, Mirrors, Towel Bars, Medicine Cabinets | S&C | Check for black spots, scratches, cat-eves, chips, and other defects.
10.0 Interior Finishes | 10.12 Shower Doors, Mirrors, Towel Bars, Medicine Cabinets | S&C | Check for correct size and location.
10.0 Interior Finishes | 10.12 Shower Doors, Mirrors, Towel Bars, Medicine Cabinets | S&C | Check spacing and types of clips. Note: FHA VA requires double clips.
10.0 Interior Finishes | 10.12 Shower Doors, Mirrors, Towel Bars, Medicine Cabinets | S&C | Make sure the mirror channel is properly cut—nor too long to cause a safety hazard from a sharp edge on the aluminum channel.
10.0 Interior Finishes | 10.13 Door Hardware / Finish Hardware | S&C
10.0 Interior Finishes | 10.13 Door Hardware / Finish Hardware | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.13 Door Hardware / Finish Hardware | Com | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.13 Door Hardware / Finish Hardware | S&C | Review all trim and material with the client and subcontractor prior to installation for location and selection and make sure all work is performed in a workman like manner
10.0 Interior Finishes | 10.13 Door Hardware / Finish Hardware | S&C | Review material and locations with the client and subcontractor prior to installation
10.0 Interior Finishes | 10.13 Door Hardware / Finish Hardware | S&C | Review problem areas such as door stops and cabinet drawers and knobs
10.0 Interior Finishes | 10.13 Door Hardware / Finish Hardware | S&C | Check operation of ALL hardware
10.0 Interior Finishes | 10.14 Stairway Railings, Balusters, Handrails | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.14 Stairway Railings, Balusters, Handrails | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.14 Stairway Railings, Balusters, Handrails | S&C | Check for proper material
10.0 Interior Finishes | 10.14 Stairway Railings, Balusters, Handrails | S&C | Check for correct spacing and heights according to current code
10.0 Interior Finishes | 10.14 Stairway Railings, Balusters, Handrails | S&C | Check for proper installation
10.0 Interior Finishes | 10.14 Stairway Railings, Balusters, Handrails | S&C | Check current code for correct balcony railing heights
10.0 Interior Finishes | 10.14 Stairway Railings, Balusters, Handrails | S&C | Check for proper strength and anchoring
10.0 Interior Finishes | 10.14 Stairway Railings, Balusters, Handrails | S&C | Check for correct spacing of pickets per plan and code
10.0 Interior Finishes | 10.15 Windows | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.15 Windows | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.15 Windows | S&C | Confirm hardware is correct
10.0 Interior Finishes | 10.16 Flooring Installation - Carpet | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.16 Flooring Installation - Carpet | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.16 Flooring Installation - Carpet | S&C | Check with flooring contractor to verify type, style, manufacturer, quality, and color of carpet.
10.0 Interior Finishes | 10.16 Flooring Installation - Carpet | S&C | Make sure tack strip is nailed.
10.0 Interior Finishes | 10.16 Flooring Installation - Carpet | S&C | Check for right type of pad and glue.
10.0 Interior Finishes | 10.16 Flooring Installation - Carpet | S&C | Make sure seams are correct and trimmed.
10.0 Interior Finishes | 10.16 Flooring Installation - Carpet | S&C | Make sure carpet is stretched.
10.0 Interior Finishes | 10.16 Flooring Installation - Carpet | S&C | Make sure carpet layers do not take out or damage window screens when they run their power cords into the house.
10.0 Interior Finishes | 10.16 Flooring Installation - Carpet | S&C | Make sure any doors removed by flooring subcontractor are replaced.
10.0 Interior Finishes | 10.16 Flooring Installation - Carpet | S&C | Check doors immediately after carpet is laid to determine if any doors need to be cut down.
10.0 Interior Finishes | 10.17 Flooring Installation - Vinyl | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.17 Flooring Installation - Vinyl | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
10.0 Interior Finishes | 10.18 Flooring Installation - Hardwood Flooring | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.18 Flooring Installation - Hardwood Flooring | S&C | Have slab foundations prepped and leveled and moisture conditions checked before starting floors.
10.0 Interior Finishes | 10.18 Flooring Installation - Hardwood Flooring | S&C | Have all slab foundations sealed with bondex or similar product.
10.0 Interior Finishes | 10.18 Flooring Installation - Hardwood Flooring | S&C | Review layout and materials with the client and subcontractor including the direction of the flooring before starting.
10.0 Interior Finishes | 10.18 Flooring Installation - Hardwood Flooring | S&C | Make sure all materials have been in the conditioned building for at least a week before installation.
10.0 Interior Finishes | 10.18 Flooring Installation - Hardwood Flooring | S&C | Use headers at all doors and openings where possible
10.0 Interior Finishes | 10.18 Flooring Installation - Hardwood Flooring | S&C | Make stain samples for the client and discuss the sheen of the finish material.
10.0 Interior Finishes | 10.18 Flooring Installation - Hardwood Flooring | S&C | Always leave a gap at the edges for expansion.
10.0 Interior Finishes | 10.18 Flooring Installation - Hardwood Flooring | S&C | Always protect the floors after the finish materials have dried sufficiently.
10.0 Interior Finishes | 10.19 Temporary Utilities Conversion | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.20 Lightweight Concrete | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.20 Lightweight Concrete | S&C | When using lightweight concrete: Confirm all decks, walls, and sub floors have been plugged
10.0 Interior Finishes | 10.20 Lightweight Concrete | S&C | When using lightweight concrete: Repair any damage to the drywall before pouring
10.0 Interior Finishes | 10.20 Lightweight Concrete | S&C | When using lightweight concrete: Make sure area is swept out
10.0 Interior Finishes | 10.20 Lightweight Concrete | S&C | When using lightweight concrete: Confirm that all toilet rings are at proper height and that they are backed with 3/4" plywood
10.0 Interior Finishes | 10.20 Lightweight Concrete | S&C | When using lightweight concrete: Double check that the lightweight slab is the correct thickness
10.0 Interior Finishes | 10.20 Lightweight Concrete | Com | When using lightweight concrete: Schedule inspection of subfloor before pouring
10.0 Interior Finishes | 10.21 Plaster | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
10.0 Interior Finishes | 10.21 Plaster | S&C | Maintain proper moisture so that the plaster can cure correctly
10.0 Interior Finishes | 10.21 Plaster | S&C | Confirm that there aren't any voids in the plaster and make sure that the finish coat is only one-eight inch thick. Correct any damage and patch holes before color coat.
10.0 Interior Finishes | 10.21 Plaster | S&C | Scratch the surface of the brown coat with a 16-D nail to check for hardness. A gouge into the plaster means that it has not cured enough whereas a scrape along the top means it has.
10.0 Interior Finishes | 10.21 Plaster | S&C | Check for any cracks in the brown coat
10.0 Interior Finishes | 10.21 Plaster | S&C | Check for any over-spray of paint on brown coat that would destroy the bond
10.0 Interior Finishes | 10.21 Plaster | S&C | Confirm that no outlets have been covered
10.0 Interior Finishes | 10.21 Plaster | S&C | After the seven-day cure time, inspect the brown coat
11.0 MEP Trimout | 11.0 MEP Trimout - General | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
11.0 MEP Trimout | 11.0 MEP Trimout - General | S&C | Coordination Meeting with all trades during this phase of construction prior to start
11.0 MEP Trimout | 11.1 Fireplace Finish | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
11.0 MEP Trimout | 11.2 Electrical Finish | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
11.0 MEP Trimout | 11.2 Electrical Finish | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
11.0 MEP Trimout | 11.2 Electrical Finish | S&C | Check the product specifications and layout with the client and subcontractor before installation
11.0 MEP Trimout | 11.2 Electrical Finish | S&C | Make sure all exterior lighting is either fluorescent or on a photo cell
11.0 MEP Trimout | 11.2 Electrical Finish | S&C | Make sure all closet lighting is installed per code
11.0 MEP Trimout | 11.2 Electrical Finish | S&C | Make sure all electrical trim and fixtures meet local codes and title 24
11.0 MEP Trimout | 11.3 Plumbing Finish | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
11.0 MEP Trimout | 11.3 Plumbing Finish | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
11.0 MEP Trimout | 11.3 Plumbing Finish | S&C | Check the product specifications and layout with the client and subcontractor before installation
11.0 MEP Trimout | 11.3 Plumbing Finish | S&C | Double check layout with client before slabs are drilled
11.0 MEP Trimout | 11.4 HVAC Finish | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
11.0 MEP Trimout | 11.4 HVAC Finish | S&C | Verify whether duct testing is required - complete if necessary
11.0 MEP Trimout | 11.4 HVAC Finish | S&C | Review registers and flow direction with client and subcontractor prior to installation
11.0 MEP Trimout | 11.4 HVAC Finish | S&C | Check underfloor ducting for damage caused during construction
11.0 MEP Trimout | 11.4 HVAC Finish | S&C | Make sure all registers are installed in a workmanlike manner
11.0 MEP Trimout | 11.4 HVAC Finish | S&C | Paint all sheet metal boots flat black prior to installing the registers
11.0 MEP Trimout | 11.4 HVAC Finish | S&C | Check all equipment for proper clearances
11.0 MEP Trimout | 11.5 Fire Protection Finish | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
11.0 MEP Trimout | 11.6 Equipment Startup | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
11.0 MEP Trimout | 11.7 Appliance Installation and Startup | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
11.0 MEP Trimout | 11.7 Appliance Installation and Startup | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
11.0 MEP Trimout | 11.7 Appliance Installation and Startup | S&C | Review with client and subcontractor prior to installation
11.0 MEP Trimout | 11.7 Appliance Installation and Startup | S&C | Make sure the installer is certified
11.0 MEP Trimout | 11.7 Appliance Installation and Startup | S&C | Save all literature for home owners warranty box
11.0 MEP Trimout | 11.7 Appliance Installation and Startup | S&C | Make sure all appliances are to the proper height
11.0 MEP Trimout | 11.8 Security System Finish | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
11.0 MEP Trimout | 11.9 Central Vacuum Finish | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
12.0 Finish Sitework | 12.1 Finish grading | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
12.0 Finish Sitework | 12.1 Finish grading | S&C | Make sure all Property lines are staked and verified before starting any work.
12.0 Finish Sitework | 12.1 Finish grading | S&C | Remove Erosion control devices and save if possible for future protection.
12.0 Finish Sitework | 12.1 Finish grading | S&C | Locate and check existing drainage to make sure it is clear and operational.
12.0 Finish Sitework | 12.1 Finish grading | S&C | Locate and verify meter locations on house and at property lines and review with owner and subcontractor.
12.0 Finish Sitework | 12.1 Finish grading | S&C | Review drawings and trench design and specifications with the subcontractor and representative of the utility co.
12.0 Finish Sitework | 12.1 Finish grading | S&C | Make sure you have a minimum of 8”earth to wood (mudsill) contact at all structures.
12.0 Finish Sitework | 12.1 Finish grading | S&C | Review Civil Engineer and landscape drawings with the client and Subcontractor for accuracy.
12.0 Finish Sitework | 12.1 Finish grading | S&C | Locate and verify all retention and filtration basins/ponds locations with the Client and subcontractor.
12.0 Finish Sitework | 12.1 Finish grading | S&C | When possible try and have the finish grading inspected prior to planting.
12.0 Finish Sitework | 12.2 Landscaping | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
12.0 Finish Sitework | 12.2 Landscaping | S&C | Review the site and Landscaping plan with the Client and subcontractor prior to starting any work.
12.0 Finish Sitework | 12.2 Landscaping | S&C | Verify property lines with client and subcontractor prior to starting work.
12.0 Finish Sitework | 12.2 Landscaping | S&C | Use drip irrigation at the building and if spray heads are used make sure they DO NOT spray towards the building.
12.0 Finish Sitework | 12.2 Landscaping | S&C | Review areas of drainage when complete for access and operation.
12.0 Finish Sitework | 12.3 Concrete - Exterior | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
12.0 Finish Sitework | 12.4 Decorative Retaining Walls | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
12.0 Finish Sitework | 12.5 Fencing | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
12.0 Finish Sitework | 12.5 Fencing | S&C | Review the site and Landscaping plan with the Client and subcontractor prior to starting any work.
12.0 Finish Sitework | 12.5 Fencing | S&C | Verify property lines with client and subcontractor prior to starting work.
12.0 Finish Sitework | 12.6 Driveway Flatwork (Paving - Asphalt) | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
12.0 Finish Sitework | 12.6 Driveway Flatwork (Paving - Asphalt) | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
12.0 Finish Sitework | 12.6 Driveway Flatwork (Paving - Asphalt) | S&C | Review with the Client and subcontractor specifications, the location, finish, color, layout and score joints, and clearances prior to starting work.
12.0 Finish Sitework | 12.6 Driveway Flatwork (Paving - Asphalt) | S&C | Add sleeves under flatwork for future access across and under paving.
12.0 Finish Sitework | 12.7 Driveway Flatwork (Paving - Concrete) | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
12.0 Finish Sitework | 12.7 Driveway Flatwork (Paving - Concrete) | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
12.0 Finish Sitework | 12.7 Driveway Flatwork (Paving - Concrete) | S&C | Review with the Client and subcontractor specifications, the location, finish, color, layout and score joints, and clearances prior to starting work.
12.0 Finish Sitework | 12.7 Driveway Flatwork (Paving - Concrete) | S&C | Add sleeves under flatwork for future access across and under paving.
12.0 Finish Sitework | 12.8 Driveway Flatwork (Paving - Pervious) | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
12.0 Finish Sitework | 12.8 Driveway Flatwork (Paving - Pervious) | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
12.0 Finish Sitework | 12.8 Driveway Flatwork (Paving - Pervious) | S&C | Review with the Client and subcontractor specifications, the location, finish, color, layout and score joints, and clearances prior to starting work.
12.0 Finish Sitework | 12.8 Driveway Flatwork (Paving - Pervious) | S&C | Add sleeves under flatwork for future access across and under paving.
12.0 Finish Sitework | 12.9 Swimming Pool | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
12.0 Finish Sitework | 12.9 Swimming Pool | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
12.0 Finish Sitework | 12.10 Flatwork - Concrete | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
12.0 Finish Sitework | 12.10 Flatwork - Concrete | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
12.0 Finish Sitework | 12.11 Flatwork - Stone | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
12.0 Finish Sitework | 12.11 Flatwork - Stone | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
12.0 Finish Sitework | 12.11 Flatwork - Stone | S&C | Review with the Client and subcontractor specifications, the location, finish, color, layout and score joints, and clearances prior to starting work.
12.0 Finish Sitework | 12.11 Flatwork - Stone | S&C | Add sleeves under flatwork for future access across and under paving.
12.0 Finish Sitework | 12.12 Flatwork - Pavers | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
12.0 Finish Sitework | 12.12 Flatwork - Pavers | S&C | Review selection with subcontractor prior to arrival on site. Once on site, verify that it is correct against the selection
12.0 Finish Sitework | 12.12 Flatwork - Pavers | S&C | Review with the Client and subcontractor specifications, the location, finish, color, layout, and clearances prior to starting work.
12.0 Finish Sitework | 12.12 Flatwork - Pavers | S&C | Add sleeves under flatwork for future access across and under paving.
12.0 Finish Sitework | 12.12 Flatwork - Pavers | S&C | Verify subgrade requirements
13.0 Final Clean Up | 13.1 Superintendent Pre-Final Walk-thru | S&C | Walk the project room by room including the exterior and make a list of deficiencies
13.0 Final Clean Up | 13.1 Superintendent Pre-Final Walk-thru | S&C | Concentrate on one room at a slab and make list as complete as possible
13.0 Final Clean Up | 13.1 Superintendent Pre-Final Walk-thru | S&C | Pay close attention to health and safety issues, stairs, railing, smoke detectors
13.0 Final Clean Up | 13.1 Superintendent Pre-Final Walk-thru | S&C | Review the conditions of approval from the city and or count and make sure we are in compliance with them
13.0 Final Clean Up | 13.1 Superintendent Pre-Final Walk-thru | S&C | Review and make sure all engineering and peer inspections are complete and backed up, send all that haven’t been previously to the city or county inspector
13.0 Final Clean Up | 13.1 Superintendent Pre-Final Walk-thru | S&C | Check for squeaky floors
13.0 Final Clean Up | 13.1 Superintendent Pre-Final Walk-thru | S&C | Have drywall and paint touched up
13.0 Final Clean Up | 13.1 Superintendent Pre-Final Walk-thru | S&C | Run and test all systems including: Dishwasher,HVAC system, Range / cooktop, Ovens, Refrigerator / wine coolers, Pool and Spa equipment and covers, Landscape sprinkler system / gates / wells, Audio Visual systems, Alarm, Garage doors / remotes coded, Hot water heater / recirculating pumps, All plumbing fixtures / garage disposals, Electrical outlets / lighting and systems / solar system / fans, All drainage systems including supporting sumps and pumps, Whirlpool tubs, Install and adjust any and all doors and hardware and bath accessories, All exterior doors and windows / skylights, Fireplaces / BBQ, Hydronic / warm floor systems
13.0 Final Clean Up | 13.1 Superintendent Pre-Final Walk-thru | Com | Schedule and have interior and exterior of home cleaned before client walk through
13.0 Final Clean Up | 13.1 Superintendent Pre-Final Walk-thru | S&C | Have home final by inspection department prior to client walk through
13.0 Final Clean Up | 13.2 Punchlist and Repair | S&C | Ask clients to attend alone to have minimal distractions so they can concentrate on their home
13.0 Final Clean Up | 13.2 Punchlist and Repair | S&C | Walk room by room and go through all systems to demonstrate the operation to the clients and compile a complete punch list
13.0 Final Clean Up | 13.2 Punchlist and Repair | S&C | Have the customer service / warranty representative to go through systems and compile a complete punch to be reviewed and compiled with superintendents list after the walk through, have clients sign the punch list
13.0 Final Clean Up | 13.2 Punchlist and Repair | S&C | Send a copy of the completed punch list to the client for their review and add any items they have that aren’t on our list
13.0 Final Clean Up | 13.3 Home Interior Cleaning | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
13.0 Final Clean Up | 13.3 Home Interior Cleaning | S&C | In multi-family or attached units, make sure all debris touching drywall, plaster, or studs at all sound or party wall conditions is removed
13.0 Final Clean Up | 13.4 Exterior Cleaning | Com | Preconstruction meeting - review scope, safety, coordination, site logistics
13.0 Final Clean Up | 13.5 Miscellaneous | S&C | Check for Squeaky Floors
13.0 Final Clean Up | 13.6 Homeowner Orientation | S&C | Review the completed list with the clients and demonstrate to the function and operation of doors, windows, and all systems including pool and exterior systems and answer any questions the clients may have.
13.0 Final Clean Up | 13.6 Homeowner Orientation | Com | Have the client sign off on the completed list.
13.0 Final Clean Up | 13.6 Homeowner Orientation | S&C | Homeowner’s literature and service manual box - Have box complete and ready to review and hand off to clients at walk through / punch list
13.0 Final Clean Up | 13.6 Homeowner Orientation | S&C | Make sure all as builts and product literature including subcontractor list included